## Table 1
| MajorActivity | PercentComplete
1 | Mobilization â€“ Civil Early Works only | 100%
2 | Surveying â€“ Civil Early Works only | 100%
3 | Tree Clearing and Mulching | 100%
4 | Fabrication (off-site) Piping Spools | 100%
5 | Hydro-Vac/Excavation â€“ Civil Early Works only | 100%
6 | Road Strip | 100%
7 | Road Cut/Fill | 100%
8 | Install Road Pitrun | 100%
9 | Road Subgrade Preparation | 100%
10 | Piling | 100%
11 | Installation of HPG Piping | 95%
12 | Cooler Installation | 99%
13 | Backfill | 93%
14 | Tie-Ins | 95%
15 | Final Clean Up | 10%
16 | Testing | 50%
17 | Commissioning | 13%

## Table 2
LiegeLateral
1 |  | Leismer East CS | Loop
2 |  | Reporting Period | Reporting Period
3 | Description | /Total | /Total
4 | Near Hits | 0/3 | 0/4
5 | Minor | 0/12 | 0/42
6 | Serious | 0/0 | 0/0
7 | Major | 0/0 | 0/0
8 | Critical | 0/0 | 0/0
9 | Note: Reference TransCanada Incident Classification Guide â€“
10 | Environmental section for incident descriptions.
11 |  | Leismer East CS | Loop
12 |  | Reporting | Reporting
13 | Description | Period/Total | Period/Total
14 | Near Hits | 0/4 | 0/15
15 | Minor | 2/36 | 0/62
16 | Serious | 0/1 | 0/2
17 | Major | 0/0 | 0/0
18 | Critical | 0/0 | 0/0
19 | Note: Reference TransCanada Incident Classification Guide â€“ Safety/Security
20 | sections for descriptions.