## Table 1
| Activity | PercentComplete
1 | Construction of camp site | 100
2 | Preparation of laydown yards | 100
3 | Preparation of existing and temporary access | 100
4 | Clearing KP 59 â€“ 91 | 100
5 | Grading | 100
6 | Stringing | 100
7 | Bend and Setup | 100
8 | Welding | 100
9 | Coating | 100
10 | Ditching | 100
11 | Lower-in | 100
12 | Backfill | 99
13 | Tie-ins | 100
14 | Hydrostatic Testing (mainline) | 100
15 | Caliper Pigging | 100
16 | Final Tie-ins | 40
17 | Machine Cleanup | 95