## Table 1
| Activity | Spread1 | Spread2 | Spread3
1 |  | % Complete | % Complete | % Complete
2 | Preparation of laydown yards and camps | 100 | 100 | 100
3 | Preparation of existing and temporary access | 100 | 100 | 100
4 | Clearing | 100 | 100 | 100
5 | Grading | 100 | 100 | 100
6 | Stringing | 100 | 100 | 100
7 | Bend and Setup | 100 | 100 | 100
8 | Poor Boy Welding | 100 | N/A | N/A
9 | Mainline Welding | 100 | 100 | 100
10 | Coating | 98 | 100 | 100
11 | Ditching | 98 | 100 | 100
12 | Lower-in | 98 | 100 | 100

## Table 2
|  |  | Spread1 | Spread2 | Spread3
1 |  | Activity | % Complete | % Complete | % Complete
2 | Backfill |  | 98 | 100 | 100
3 | Tie-ins |  | 98 | 100 | 100
4 | Road/Pipeline Bores |  | 100 | 100 | 100
5 | Hydrostatic Testing |  | 82 | 100 | 100
6 | Caliper Pigging |  | 82 | 100 | 100
7 | Final Tie-ins |  | 0 | 100 | 100
8 | Cleanup |  | 21 | 70 | 99

## Table 3
DescriptionReportingPeriodTotal
1 | Safe Acts | 0/277
2 | Unsafe Acts | 0/120
3 | Safety 24/7 | 0/8
4 | Near Hits | 0/2
5 | Minor | 5/504
6 | Serious | 0/46
7 | Major | 0/1
8 | Critical | 0/1
9 | Note: For incident descriptions, see TC Energy Incident Classification Guide, Safety/Security sections.

## Table 4
| Station | Activity | PercentComplete
1 | Groundbirch Compressor Station | Pipe Fabrication | 100
2 |  | Structural Steel Fabrication | 95
3 |  | Site Survey Sweep | 100
4 |  | Site Clearing/Grading | 90
5 |  | Site Backfilling Rough Grade | 100
6 |  | Site Piling | 95
7 |  | Pile Cutting and Capping | 95
8 |  | Pipe Installation | 90
9 |  | Compressor Unit Foundation (sub-grade) | 100
10 |  | Compressor Unit Foundation (concrete) | 100
11 |  | Compressor Building Envelope | 100
12 |  | Compressor and Turbine Installation | 50
13 |  | Compressor Package Final Installation | 30
14 |  | Compressor Building Concrete | 100
15 |  | Site Electrical Installation | 50
16 |  | Prime Contractor Mobilization | 100
17 | Saturn Compressor Station | Pipe Fabrication | 25
18 |  | Structural Steel Fabrication | 25
19 |  | Site Survey Sweep | 100
20 |  | Site Clearing/Grading | 90
21 |  | Site Backfilling Rough Grade | 75
22 |  | Site Piling | 95
23 |  | Pile Cutting and Capping | 60
24 |  | Pipe Installation | 0
25 |  | Compressor Unit Foundation (sub-grade) | 0
26 |  | Compressor Unit Foundation (concrete) | 0
27 |  | Compressor Building Envelope | 0
28 |  | Compressor and Turbine Installation | 0
29 | Altares Receipt Meter Station | Pipe Fabrication | 100
30 |  | Site Clearing | 100
31 |  | Site Stripping and Grading | 80
32 |  | Prime Contractor Mobilization | 100
33 |  | Pile Driving | 100
34 |  | Piping Installation | 100
35 |  | Coating | 10
36 |  | Electrical Installation | 90
37 |  | Hydrotesting | 100
38 |  | Backfilling | 5
39 |  | Fencing | 0
40 |  | Clean-up/Gravel | 0
41 |  | Prime Contractor De-Mobilization | 0
42 | Gundy Receipt Meter Station | Pipe Fabrication | 100
43 |  | Site Clearing | 100
44 |  | Site Stripping and Grading | 100
45 |  | Prime Contractor Mobilization | 100
46 |  | Pile Driving | 100
47 |  | Piping Installation | 100
48 |  | Coating | 100
49 |  | Electrical Installation | 100
50 |  | Hydrotesting | 100
51 |  | Backfilling | 100
52 |  | Fencing | 100
53 |  | Clean-up/Gravel | 100
54 |  | Prime Contractor De-Mobilization | 100

## Table 5
DescriptionReportingPeriodTotal
1 | Safe Acts | 3/37
2 | Unsafe Acts | 1/10
3 | Safety 24/7 | 0/1
4 | Near Hits | 0/0
5 | Minor | 0/4
6 | Serious | 0/0
7 | Major | 0/0
8 | Critical | 0/0
9 | Note: For incident descriptions, see TC Energy Incident Classification Guide, Safety/Security sections.