## Table 1
LEGAL INSTRUMENT CONCORDANCE WITH NEB CONDITION 106: CONSTRUCTION PROGRESS REPORTS
NEB Condition 106 | OC-065 (CPCN) | AO-005- OC-2 (OC2) | AO-004-OC-49 (OC49) | AO-001-XO- T260-007- 2016 (TEMP) | AO-002-XO- T260-008- 2016 (PUMP1) | AO-002-XO- T260-009- 2016 (PUMP2) | AO-001-XO- T260-010- 2016 (TANKS) | AO-001-MO- 015-2016 (DEACT)
Trans Mountain must file w ith the NEB, monthly construction progress reports from com m encing construction until after com m encing operations. The reports must include information on the progress of activ ities carried out during the reporting period, including: | See below . | N/A – No activ ities occurred during this reporting period. | N/A – No activ ities under this legal instrument occurred during this reporting period. | See below . | N/A – No activ ities occurred during this reporting period. | N/A – No activ ities occurred during this reporting period. | N/A – No activ ities occurred during this reporting period. | N/A – No activ ities occurred during this reporting period.
a) safety , env ironmental and security issues, or non- compliances that occurred during the reporting period; | Refer to section 4.0 | See abov e. | See abov e. | N/A to this reporting period | See abov e. | See abov e. | See abov e. | See abov e.
b) measures undertaken to resolv e safety and env ironmental issues or non-compliances identified in a); | Refer to Section 4.2 | See abov e. | See abov e. | N/A to this reporting period | See abov e. | See abov e. | See abov e. | See abov e.
c) confirmation that security issues identified in a) have been addressed; | N/A to this reporting period | See abov e. | See abov e. | N/A to this reporting period | See abov e. | See abov e. | See abov e. | See abov e.
d) a description and the location of any change made to geohazard mitigation measures pursuant to Condition 51; and | N/A to this reporting period | See abov e. | See abov e. | N/A to this reporting period | See abov e. | See abov e. | See abov e. | See abov e.
e) the location of any pressure tests carried out during the reporting period and a description of any unsuccessful pressure tests, including the reasons for the lack of success of each. | N/A to this reporting period | See abov e. | See abov e. | N/A to this reporting period | See abov e. | See abov e. | See abov e. | See abov e.

## Table 2
TOTAL NUMBER OF SAFETY, ENVIRONMENTAL, SECURITY AND NON-COMPLIANCE ISSUES FOR THIS REPORTING PERIOD
Description | Total Number of Issues
Medical Aids | 0
Lost Time Incidents | 0
Higher Potential Near Miss | 0
Property Damage (> $5,000) | 0
Other | 0
Environmental Issues | 0
Security | 0
Non-Compliance (Spills) | 2

## Table 3
PROJECT WORK AREAS
Phase # | Phased Construction Spreads, Regions, or Work Areas | Phase Activity
Terminals
1 | Westridge Marine Terminal | MOBILIZATION STARTED FOR OFFSHORE; LIMITED ONSHORE WORK COMMENCED
2 | Edmonton Terminal | NOT STARTED
3 | Sumas Terminal | NOT STARTED
4 | Burnaby Terminal | STARTED
Line 1 Pumps
5 | Jasper Pump Station | NOT STARTED
6 | Black Pines Pump Station | NOT STARTED
7 | Kamloops Pump Station 1 | NOT APPLICABLE
8 | Sumas Pump Station 1 | NOT APPLICABLE
Line 2 Pumps
9 | Edmonton Pump Station | NOT STARTED
10 | Gainford Pump Station | NOT STARTED
11 | Wolf Pump Station | NOT STARTED
12 | Edson Pump Station | NOT STARTED
13 | Hinton Pump Station | NOT STARTED
14 | Blue River Pump Station | NOT STARTED
15 | McMurphy Pump Station | NOT STARTED
16 | Blackpool Pump Station | NOT STARTED
17 | Black Pines Pump Station | NOT STARTED
18 | Kamloops Pump Station | NOT STARTED
19 | Kingsvale Pump Station | NOT STARTED
20 | Niton Pump Station Reactivation 2 | NOT APPLICABLE
Line 1 Reactivation / Deactivation / Other Activities
21 | Line 1 (valves) 3 | NOT STARTED
22 | Hinton to BC Border Reactivation | NOT STARTED
23 | BC Border to Hargreaves Reactivation | NOT STARTED
24 | Darfield to Black Pines Reactivation | NOT STARTED
25 | Wolf Pump Station Deactivation 2 | NOT APPLICABLE
Line 2 Work Areas
26 | Spread 1 | NOT STARTED
27 | Spread 2 | SAFE SHUT DOWN
28 | Spread 3 | NOT STARTED
29 | Spread 4 | NOT STARTED
30 | Spread 5 | NOT STARTED
31 | Spread 5, Condition 39 Coldw ater Hydrological | NOT STARTED
32 | Spread 5, Condition 7 Ohamil | NOT STARTED
33 | Spread 6 | NOT STARTED
34 | Spread 6, Condition 7 Tzeachten | NOT STARTED
35 | Spread 6, Condition 77 Lightning Rock | NOT STARTED
36 | Spread 7 | NOT STARTED
37 | Spread 7, Condition 7 Surrey Bend | NOT STARTED
38 | Westridge Delivery Lines | NOT STARTED
39 | Burnaby Tunnel | SAFE SHUT DOWN

## Table 10
Temporary Infrastructure: Pursuant to Condition 61 Filing (Filing IDs A88496, A95098, C01116, C02063)
Spread 1 | SAFE SHUT DOWN
Spread 2 | SAFE SHUT DOWN
Spread 3 | SAFE SHUT DOWN
Spread 4 | SAFE SHUT DOWN
Spread 5 | SAFE SHUT DOWN
Spread 6 | NOT STARTED
Spread 7 | SAFE SHUT DOWN

## Table 11
Construction Progress Onshore: Mobilization under OC-065 has commenced:  Civil w orks for temporary construction offices and infrastructure w ere initiated; and  Water Treatment equipment w as set in place. Foreshore: Turbidity curtains and foreshore sediment control measures continue to be monitored and maintained w here rip-rap w as removed east of Pier 59. Sheet Piles: Complete for safe shutdow n during w hich:  All sheet piles for Cells 6, 7, and 9 w ere driven to depth and accepted, completing circular cell perimeter; total of 396 sheet piles  Cells 6, 7 and 9 w ere filled w ith aggregate to stabilize cells for safe shutdow n Marine Berth Piles : Complete for safe shutdow n, during w hich  Piles for Mooring Dolphins MD4, MD5 and MD6 driven to depth, accepted and capped for safe shutdow n; total of 12 piles  Piles for Trestle Bent TS5 driven to depth, accepted and capped for safe shutdow n; total of 2 piles  Piles for Loading Platform LP1-2 driven to depth, accepted and capped for safe shutdow n; total of 14 piles
PHASE 1: WESTRIDGE MARINE TERMINAL
Issues and Non-Compliances
Safety Issue | Security Issue | Environm ent Issue | Non-compliance
0 | 0 | 0 | 0

## Table 12
PHASE 2 : EDMONTON TERMINAL
Issues and Non-Compliances
Safety Issue | Security Issue | Environm ent Issue | Non-compliance
0 | 0 | 0 | 0

## Table 13
PHASE 4: BURNABY TERMINAL
Issues and Non-Compliances
Safety Issue | Security Issue | Environm ent Issue | Non-compliance
0 | 0 |  No Environmental Issues or Events  20 Environmental Deficiencies identified this reporting period (Section 4.1). |  2 non-compliances identified this reporting period (Section 4.2).

## Table 14
Environmental Deficiencies (Near Misses)
Description | Total Number of Issues
Land & Soil (i.e., erosion, subsidence, topsoil loss/degradation, soil compaction, admixing, rutting) | 9
Vegetation (i.e., w eeds, improper clearing/brushing, improper pesticide use, incorrect seed mix, herbicide release, Clubroot) | 0
Water (i.e., improper w ater discharge, sedimentation/turbidity exceedances, bank slumping, w atercourse geomorphology changes) | 5
Air & Noise (i.e., attributable/indeterminate odours or noise, air quality exceedances) | 0
Fish & Wildlife (i.e., habitat disturbance/destruction, impacted fish/w ildlife/migratory birds/Species at Risk) | 1
Waste & Hazardous Materials (i.e., improper storage, disposal, or shipping document completion) | 5
Contamination (i.e., discovery of contaminated soil/groundw ater, attributable/indeterminate sheen) *Excludes contamination from new releases | 0
Heritage Resources (i.e., unauthorized disturbance of new ly discovered/know n heritage resources) | 0

## Table 15
Non-compliance Summary
ID # | Description | Date | Measures Taken
Loc.4.18.ENV.09 1819.00000471 | At approximately 7:30 AM, a sump overflow ed, resulting in a discharge of w ater bypassing authorized w ater treatment w orks into w atercourse BC-785j resulting in a non-compliance w ith Waste Discharge Permit 6945. Continuous w ater quality monitoring in place did not indicate a spike in turbidity levels and no adverse effects to the environment or human health w ere observed. | 18 September 2019 | Initial response: Additional pumps w ere installed upon observation of the release. Contact w ater w as pumped to grassy areas to filter out any fine particulates. Long term actions: An emergency overflow pipe has been installed in the sump that overflow ed to divert any unplanned overflow to the south, aw ay from the inlet to the w atercourse.
Loc.4.18.ENV.09 2219.00000488 | At approximately 9:30 AM, a 2” pump mechanically failed w hich resulted in the discharge of turbid w ater bypassing w ater treatment w orks to w atercourse BC-785k from the Upper Road ditch resulting in a non-compliance w ith Waste Discharge Permit 6945. One 2” pump continued to direct most of the contact w ater aw ay from w atercourse BC-785k. Increased turbidity w as observed in w atercourse BC-785k for approximately 1 hour. No adverse effects to the environment or human health w ere observed. | 22 September 2019 | Initial response: Crew s w ere immediately dispatched to collect a replacement pump. The pump w as replaced and contact w ater w as then redirected aw ay from the w atercourse by 10:25 AM. Additional back-up pumps and generators w ere added to the location in case of an increase in rainfall. Water samples w ere taken from the inlet, the discharge location, and the outlet of the w atercourse flow ing through the Burnaby Terminal. Crew s monitored the site and had a shift present throughout the night. All w ork in the immediate area w as suspended temporarily to review and adjust w here required, erosion and sediment control measures. Long-term actions: All critical sumps w ill now have tw o pumps (one primary and one backup) on different float levels. More frequent site inspection w ill be implemented during expected rain events.

## Table 16
PHASE 27: SPREAD 2
Issues and Non-Compliances
Safety Issue | Security Issue | Environm ent Issue | Non-compliance
0 | 0 | 0 | 0

## Table 17
PHASE 30: SPREAD 5
Issues and Non-Compliances
Safety Issue | Security Issue | Environm ent Issue | Non-compliance
0 | 0 | 0 | 0

## Table 18
PHASE 39: BURNABY TUNNEL
Issues and Non-Compliances
Safety Issue | Security Issue | Environm ent Issue | Non-compliance
0 | 0 | 0 | 0

## Table 19
Spreads 1 and 2 – Stockpile Sites
Issues and Non-Compliances
Safety Issue | Security Issue | Environm ent Issue | Non-compliance
0 | 0 | 0 | 0

## Table 20
Spread 3 – Stockpile Sites
Issues and Non-Compliances
Safety Issue | Security Issue | Environm ent Issue | Non-compliance
0 | 0 | 0 | 0

## Table 21
Spread 4 – Stockpile Sites
Issues and Non-Compliances
Safety Issue | Security Issue | Environm ent Issue | Non-compliance
0 | 0 | 0 | 0

## Table 22
Spread 5 – Stockpile Sites
Issues and Non-Compliances
Safety Issue | Security Issue | Environm ent Issue | Non-compliance
0 | 0 | 0 | 0

## Table 23
Spread 7 – Stockpile Sites
Issues and Non-Compliances
Safety Issue | Security Issue | Environm ent Issue | Non-compliance
0 | 0 |  No Environmental Issues or Events  4 Environmental Deficiencies identified this reporting period (Section 8.5.1). | 0

## Table 24
Environmental Deficiencies (Near Misses)
Description | Total Number of Issues
Land & Soil (i.e., erosion, subsidence, topsoil loss/degradation, soil compaction, admixing, rutting) | 0
Vegetation (i.e., w eeds, improper clearing/brushing, improper pesticide use, incorrect seed mix, herbicide release, Clubroot) | 0
Water (i.e., improper w ater discharge, sedimentation/turbidity exceedances, bank slumping, w atercourse geomorphology changes) | 0
Air & Noise (i.e., attributable/indeterminate odours or noise, air quality exceedances) | 0
Fish & Wildlife (i.e., habitat disturbance/destruction, impacted fish/w ildlife/migratory birds/Species at Risk) | 1
Waste & Hazardous Materials (i.e., improper storage, disposal, or shipping document completion) | 3
Contamination (i.e., discovery of contaminated soil/groundw ater, attributable/indeterminate sheen) *Excludes contamination from new releases | 0
Heritage Resources (i.e., unauthorized disturbance of new ly discovered/know n heritage resources) | 0